## Sheet1
| Start Date | End Date
Development
Logical Data Generation Board
Generating data for any particular schema and navigate within tabs (for Single Schema with static page) | 2015-08-05 | 15/5/2015
Single tab for schema related GUI(Which is being static page) | 2015-08-05 | 15/5/2015
Link to My Dashboard Link | TOD | TOD
Logic for Generating Data and Dump into DB | 21/04/2015 | 2015-07-05
Logic for Generating Data or Reset all the fields GUI | 18/5/2015 | 22/5/2015
Pop up screen on completion of data generation with a message | 18/5/2015 | 22/5/2015
Reset page, once back from pop up screen | 18/5/2015 | 22/5/2015
My Dashboard
Displaying list of generated data summary in a grid
Result in tabular format
Check box for selection of entries shown
Download the selected record in different formats
XLS format
CSV format
PDF Format
Master Data Dictionary Creation
Create a dictionary of names, address etc
Email on successful generation of data
Quick search using request id
Admin
Project Management
User Management
Add Users
Sending email on successful creation of users
Assign user to domain
Edit users
Delete Users
Database connection to be monitorized on regular intervals
Display informative alerts if the database is not connected
Testing & Production